**Continuous Improvement Planning in 2019-20**

**for 2020-2021**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **What/When** | **Implications for my school** | **School Actions** | **Purpose** | **Outcomes/Products** |
| SuP Mid-Year Review **January** |  | * Review data from multiple sources (e.g., mid-year data, stakeholder feedback)
* Reflect on progress and determine any adjustments to plan for remainder of the year
 | Data analysis will identify if adjustments are needed to current plan. | Mid-Year SuP Review Notes and Plans |
| Comprehensive Needs Assessment**February**  |  | * Schedule and plan stakeholder feedback sessions (including T1 parent survey requirements)
* Review data from multiple sources (e.g., mid-year SuP review, stakeholder feedback, self-assessment)
* Complete and submit CNA by 2/29/20
 | Data analysis will identify strengths and needs within our 3 key priorities for 2020-2021 at both school and district levels | * CNA for 2020-2021
* Data Review Narrative for 2020-2021
 |
| School Site Visits**March** |  | * Meet with district team to review strengths, opportunities and areas of focus for 20-21
* Refine goals, PD/strategies, and monitoring for alignment
 | * Information from schools will inform present and future needs related to priorities
* School Success Plan for 2020-2021 will begin to take shape
 | Draft goals, PD/Strategies, and monitoring plan |
| Success Plan Drafts**April** |  | * Continue to refine goals, PD/strategies, and monitoring for alignment
* Title I planning
* Summer PD requests for priority schools
 | Initial PD plans, resources, and school supports will align to district priorities and school needs | * Draft Success Plan
* Summer PD Request for Priority Schools aligned to SuP goals/strategies
 |
| Success Plan Reviews**May** |  | * Use final data to evaluate efforts from last year before finalizing success plan
* Review final draft of Success Plan (peer review)
* District teams review and analyze draft School Success Plans
* Share final draft of Success Plan with Assistant Superintendent
 | School Success Plans will inform metrics, tactics and milestones in the District Success Plan  | Refine Draft Success Plan based on peer and district feedback |
| Monitor and Adjust**June** |  | School Success Plans will help refine PD, resources and school supports for school needs within the district priorities | Finalize draft Success Plan |
| Success Plans Finalized**End of July** |  | * Upload Success Plan by deadline for Board approval
* Share Success Plan with school stakeholders
 | Final Success Plans at all levels become part of ongoing continuous improvement process | Publish Success Plan |