**Continuous Improvement Planning in 2019-20**

**for 2020-2021**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **What/When** | **Implications for my school** | **School Actions** | **Purpose** | **Outcomes/Products** |
| SuP Mid-Year Review  **January** |  | * Review data from multiple sources (e.g., mid-year data, stakeholder feedback) * Reflect on progress and determine any adjustments to plan for remainder of the year | Data analysis will identify if adjustments are needed to current plan. | Mid-Year SuP Review Notes and Plans |
| Comprehensive Needs Assessment  **February** |  | * Schedule and plan stakeholder feedback sessions (including T1 parent survey requirements) * Review data from multiple sources (e.g., mid-year SuP review, stakeholder feedback, self-assessment) * Complete and submit CNA by 2/29/20 | Data analysis will identify strengths and needs within our 3 key priorities for 2020-2021 at both school and district levels | * CNA for 2020-2021 * Data Review Narrative for 2020-2021 |
| School Site Visits  **March** |  | * Meet with district team to review strengths, opportunities and areas of focus for 20-21 * Refine goals, PD/strategies, and monitoring for alignment | * Information from schools will inform present and future needs related to priorities * School Success Plan for 2020-2021 will begin to take shape | Draft goals, PD/Strategies, and monitoring plan |
| Success Plan Drafts  **April** |  | * Continue to refine goals, PD/strategies, and monitoring for alignment * Title I planning * Summer PD requests for priority schools | Initial PD plans, resources, and school supports will align to district priorities and school needs | * Draft Success Plan * Summer PD Request for Priority Schools aligned to SuP goals/strategies |
| Success Plan Reviews  **May** |  | * Use final data to evaluate efforts from last year before finalizing success plan * Review final draft of Success Plan (peer review) * District teams review and analyze draft School Success Plans * Share final draft of Success Plan with Assistant Superintendent | School Success Plans will inform metrics, tactics and milestones in the District Success Plan | Refine Draft Success Plan based on peer and district feedback |
| Monitor and Adjust  **June** |  | School Success Plans will help refine PD, resources and school supports for school needs within the district priorities | Finalize draft Success Plan |
| Success Plans Finalized  **End of July** |  | * Upload Success Plan by deadline for Board approval * Share Success Plan with school stakeholders | Final Success Plans at all levels become part of ongoing continuous improvement process | Publish Success Plan |